## Sheet1
stateid | districtid | blockid | panchayatid | villageid | schemeid | schemename | sanctionyear | type | status | estimatedcost | csrdonation | omcost | expenditure | totalcentralexpenditure | centralexpenditure_sc | centralexpenditure_st | centralexpenditure_gen | totalstateexpenditure | stateexpenditure_sc | stateexpenditure_st | stateexpenditure_gen | totalworldbankexpenditure | totalcommunityexpenditure | totalcsrexpenditure | totalotherexpenditure | noofvillages | physicalprogressinpercentage | handed_over_community_status | handed_over_community_date | category | workorderdate | household_planned | fhtc_provided | villagename | ispws | fhtc_scheme | isjjm | divisionid | divisionname | total_expenditure_during_jjm
15 | 690 | 10257 | 62044 | 150252 | 7400368 | WPP TEN providing and installation of R.O plant at Narayanpur village | 2015-2016 | PWS | Completed | 10 | 0 | 0 | 8.5 | 5 | 0.90224 | 0.4022 | 3.6956 | 3.5 | 0.77 | 0.28 | 2.45 | 0 | 0 | 0 | 0 | 1 | 100 | No | NULL | SVS | 2016-04-25 | 0 | 0 | NARAYANPUR | 1 | NULL | 0 | 6226 | YADGIR | 0
15 | 690 | 10257 | 62044 | 150252 | 8354973 | Providing MWS Scheme Near Chaya Bhagavathi Temple at Narayanpur Village in Shorapur Taluka | 2020-2021 | PWS | Completed | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 98 | No | NULL | SVS | 2021-01-25 | 0 | 0 | NARAYANPUR | 1 | NULL | 0 | 6226 | YADGIR | 0
15 | 690 | 10257 | 62044 | 150252 | 7193561 | GEN Providing Water Supply Scheme to Anganawadi at Narayanapur 2 Village | 2015-2016 | PWS | Completed | 0.75 | 0 | 0 | 0.75 | 0 | 0 | 0 | 0 | 0.75 | 0.09375 | 0.04688 | 0.60937 | 0 | 0 | 0 | 0 | 1 | 100 | No | NULL | SVS | 2015-10-01 | 0 | 0 | NARAYANPUR | 1 | NULL | 0 | 6226 | YADGIR | 0
15 | 690 | 10257 | 62044 | 150252 | 7911802 | SDP GEN Revival of MWS Scheme at Kanaka dasa chowk of Narayanpur Village in Shorapur Tq. | 2019-2020 | Augmentation | Completed | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 4 | 0.88 | 0.32 | 2.8 | 0 | 0 | 0 | 0 | 1 | 100 | No | NULL | SVS | 2019-09-03 | 0 | 0 | NARAYANPUR | 1 | NULL | 0 | 6226 | YADGIR | 4
15 | 690 | 10257 | 62044 | 150252 | 8354963 | Providing MWS Scheme in Sadar Colony at Narayanpur Village in Shorapur Taluka | 2020-2021 | PWS | Completed | 5 | 0 | 0 | 4.96 | 0 | 0 | 0 | 0 | 4.96 | 0 | 0 | 4.96 | 0 | 0 | 0 | 0 | 1 | 100 | No | NULL | SVS | 2021-01-25 | 0 | 0 | NARAYANPUR | 1 | NULL | 0 | 6226 | YADGIR | 4.96
15 | 613 | 2488 | 59983 | 143087 | 4874313 | MWS at Chikkamudawadi and Anajavadi villages | 2012-2013 | PWS | Completed | 9 | 0 | 0 | 6.7283 | 0.49797 | 0.18526 | 0 | 0.31271 | 6.2304 | 1.2171 | 0.45859 | 4.5547 | 0 | 0 | 0 | 0 | 1 | 0 | No | NULL | SVS | 2012-07-01 | 60 | 6 | CHIKKAMUDHAVAADI | 1 | Approved during mission period/ provided FHTC | 0 | 6209 | RAMANAGARA | 0
15 | 613 | 2484 | 59849 | 142117 | 8405775 | Providing FHTCs to 10 households of MANGAPATNADODDI Habitation in KANNAMANGALA village in RAMPURA Grama Panchayat in Channapatna taluk, Ramanagara District through SVS | 2021-2022 | retrofit | Ongoing | 12.08 | 0 | 0 | 1.3044 | 0.65219 | 0 | 0 | 0.65219 | 0.65218 | 0 | 0 | 0.65218 | 0 | 0 | 0 | 0 | 1 | 0 | No | NULL | SVS | 2021-12-28 | 4 | 32 | KANNAMANGALA | 1 | Approved during mission period/ provided FHTC | 1 | 6209 | RAMANAGARA | 1.3044
15 | 613 | 2484 | 59849 | 142117 | 5356771 | Drilling of Borewell to M.W.S Scheme at Angarahalli | 2012-2013 | PWS | Completed | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No | NULL | SVS | 2013-04-02 | 0 | 0 | KANNAMANGALA | 1 | NULL | 0 | 6209 | RAMANAGARA | 0
15 | 613 | 2484 | 59849 | 142117 | 6668201 | Revival of MWS Scheme at Chakkere Vaddaradoddi (General) | 2014-2015 | PWS | Completed | 4 | 0 | 0 | 3.9857 | 0 | 0 | 0 | 0 | 3.9857 | 0 | 0 | 3.9857 | 0 | 0 | 0 | 0 | 1 | 0 | No | NULL | SVS | 2014-07-22 | 0 | 0 | KANNAMANGALA | 1 | NULL | 0 | 6209 | RAMANAGARA | 0
15 | 613 | 2484 | 59849 | 142117 | 4893101 | Revival of MWS at Gollahallidoddi | 2012-2013 | PWS | Completed | 5 | 0 | 0 | 4.419 | 0.49859 | 0 | 0 | 0.49859 | 3.9204 | 0.61592 | 0.27375 | 3.0307 | 0 | 0 | 0 | 0 | 1 | 0 | No | NULL | SVS | 2012-06-05 | 26 | 0 | KANNAMANGALA | 1 | NULL | 0 | 6209 | RAMANAGARA | 0
15 | 613 | 2484 | 59849 | 142117 | 7301492 | SC COLONY Revival of MWS scheme at ANGARAHALLI(SCP) HHC 2 | 2015-2016 | PWS | Completed | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No | NULL | SVS | 2015-10-01 | 0 | 0 | KANNAMANGALA | 1 | NULL | 0 | 6209 | RAMANAGARA | 0
15 | 613 | 2484 | 59849 | 142117 | 7859633 | TFC 50(2018 19) Revival of MWS scheme at GOLLAHALLIDODDI village of RAMPURA G | 2018-2019 | PWS | Completed | 2 | 0 | 0 | 1.9722 | 0 | 0 | 0 | 0 | 1.9722 | 0 | 0 | 1.9722 | 0 | 0 | 0 | 0 | 1 | 100 | No | NULL | SVS | 2018-12-05 | 0 | 0 | KANNAMANGALA | 1 | NULL | 0 | 6209 | RAMANAGARA | 0
15 | 613 | 2484 | 59849 | 142117 | 3648158 | Extension of pIpe line in Saragurdoddi | 2011-2012 | PWS | Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No | NULL | SVS | 2011-07-15 | 0 | 0 | KANNAMANGALA | 1 | NULL | 0 | 6209 | RAMANAGARA | 0
15 | 613 | 2484 | 59849 | 142117 | 8405907 | Providing FHTCs to 14 households of KANVA I.B. Habitation in KANNAMANGALA village in RAMPURA Grama Panchayat in Channapatna taluk, Ramanagara District through SVS | 2021-2022 | retrofit | Ongoing | 20.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No | NULL | SVS | 2022-01-24 | 3 | 1 | KANNAMANGALA | 1 | Approved during mission period/ provided FHTC | 1 | 6209 | RAMANAGARA | 0
15 | 613 | 2484 | 59851 | 142124 | 6473239 | Revival of MWS Scheme at Sadahalli | 2014-2015 | PWS | Completed | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No | NULL | SVS | 2014-05-12 | 0 | 0 | SADAHALLI | 1 | NULL | 0 | 6209 | RAMANAGARA | 0
15 | 613 | 2484 | 59851 | 142124 | 5222643 | Drilling of Borewell to MWS Scheme at Sadahalli | 2012-2013 | PWS | Completed | 1 | 0 | 0 | 0.99321 | 0.99321 | 0.17878 | 0.07946 | 0.73497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No | NULL | SVS | 2012-12-17 | 0 | 0 | SADAHALLI | 1 | NULL | 0 | 6209 | RAMANAGARA | 0
15 | 613 | 2484 | 59851 | 142124 | 4891273 | Revival of MWS at Sadahalli | 2012-2013 | PWS | Completed | 5 | 0 | 0 | 4.9467 | 0 | 0 | 0 | 0 | 4.9467 | 0.89041 | 0.39574 | 3.6606 | 0 | 0 | 0 | 0 | 1 | 0 | No | NULL | SVS | 2012-06-05 | 89 | 0 | SADAHALLI | 1 | NULL | 0 | 6209 | RAMANAGARA | 0
15 | 613 | 2484 | 59851 | 142124 | 8163526 | Providing FHTC to 103 Households in SADAHALLI habitation in SADAHALLI village in channapatna taluk,Ramanagara District by augmentation through SVS(HTC TO FHTC CONNECTIONS 00) | 2020-2021 | retrofit | Ongoing | 23.16 | 0 | 0 | 20.4575 | 7.1286 | 0 | 0 | 7.1286 | 13.3289 | 6.1112 | 0 | 7.2177 | 0 | 0 | 0 | 0 | 1 | 25 | No | NULL | SVS | 2021-01-09 | 98 | 102 | SADAHALLI | 1 | Approved during mission period/ provided FHTC | 1 | 6209 | RAMANAGARA | 20.4575
15 | 613 | 2484 | 59851 | 142124 | 7538611 | Revival of PWS scheme at SADAHALLI | 2016-2017 | Augmentation | Completed | 3 | 0 | 0 | 2.9843 | 0 | 0 | 0 | 0 | 2.9843 | 0 | 0 | 2.9843 | 0 | 0 | 0 | 0 | 1 | 100 | No | NULL | SVS | 2016-11-02 | 0 | 0 | SADAHALLI | 1 | NULL | 0 | 6209 | RAMANAGARA | 0
15 | 613 | 2484 | 59851 | 142124 | 7837409 | (GOI GOK 2018)Revival of MWS scheme at SADAHALLI village | 2018-2019 | Augmentation | Completed | 2 | 0 | 0 | 1.9889 | 0.99447 | 0 | 0 | 0.99447 | 0.99446 | 0 | 0 | 0.99446 | 0 | 0 | 0 | 0 | 1 | 100 | No | NULL | SVS | 2018-09-28 | 0 | 0 | SADAHALLI | 1 | NULL | 0 | 6209 | RAMANAGARA | 0
15 | 613 | 2484 | 59861 | 142161 | 5720315 | Providing Water Supply to Anganavadi at Lambanithandya | 2013-2014 | PWS | Completed | 0.5 | 0 | 0 | 0.49851 | 0 | 0 | 0 | 0 | 0.49851 | 0.08973 | 0.03988 | 0.3689 | 0 | 0 | 0 | 0 | 1 | 0 | No | NULL | SVS | 2013-07-04 | 0 | 0 | MENASIGANAHALLI | 1 | NULL | 0 | 6209 | RAMANAGARA | 0
15 | 613 | 2484 | 59861 | 142161 | 6912946 | TFC201014 Drilling of Borewell to MWS Scheme at Lambanithandya 2 village | 2014-2015 | Spot | Completed | 1.5 | 0 | 0 | 1.4985 | 0 | 0 | 0 | 0 | 1.4985 | 0 | 0 | 1.4985 | 0 | 0 | 0 | 0 | 1 | 0 | No | NULL | MVS | 2015-03-02 | 0 | 0 | MENASIGANAHALLI | 0 | NULL | 0 | 6209 | RAMANAGARA | 0
15 | 613 | 2484 | 59861 | 142161 | 7719684 | TFCZPCEO140317 Drilling of Borewell at Lambanitandya 1 Village Bhoohalli gram panchayath | 2017-2018 | Augmentation | Completed | 1.5 | 0 | 0 | 1.4972 | 0 | 0 | 0 | 0 | 1.4972 | 0 | 0 | 1.4972 | 0 | 0 | 0 | 0 | 1 | 100 | No | NULL | SVS | 2017-08-08 | 0 | 0 | MENASIGANAHALLI | 1 | NULL | 0 | 6209 | RAMANAGARA | 0
15 | 613 | 2484 | 59861 | 142161 | 8163741 | Providing FHTC to177 HouseholdsinMENASIGANAHALLI habitation in MENASIGANAHALLIvillageinchannapatna taluk,Ramanagara District by augmentation through SVS(HTC TO FHTC CONNECTIONS 305) | 2020-2021 | retrofit | Ongoing | 77.78 | 0 | 0 | 63.6378 | 36.4875 | 16.0874 | 0 | 20.4001 | 27.1503 | 5.5691 | 0 | 21.5812 | 0 | 0 | 0 | 0 | 1 | 14 | No | NULL | SVS | 2021-01-11 | 169 | 215 | MENASIGANAHALLI | 1 | Approved during mission period/ provided FHTC | 1 | 6209 | RAMANAGARA | 63.6378
15 | 613 | 2484 | 59861 | 142161 | 466015 | Near Chandru Land | 2007-2008 | Spot | Completed | 0.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No | NULL | MVS | 2007-12-01 | 0 | 0 | MENASIGANAHALLI | 0 | NULL | 0 | 6209 | RAMANAGARA | 0
15 | 613 | 2484 | 59861 | 142161 | 7534227 | revival of MWS scheme at LAMBANI THANDYA | 2016-2017 | Augmentation | Completed | 2 | 0 | 0 | 1.999 | 0 | 0 | 0 | 0 | 1.999 | 0.57815 | 0 | 1.4208 | 0 | 0 | 0 | 0 | 1 | 100 | No | NULL | SVS | 2016-12-06 | 0 | 0 | MENASIGANAHALLI | 1 | NULL | 0 | 6209 | RAMANAGARA | 0
15 | 613 | 2484 | 59861 | 142161 | 6073324 | Drilling of Borewell to MWS Scheme at Meanasiganahalli Thandya | 2013-2014 | PWS | Completed | 1.25 | 0 | 0 | 1.2473 | 0 | 0 | 0 | 0 | 1.2473 | 0.22452 | 0.09979 | 0.92303 | 0 | 0 | 0 | 0 | 1 | 0 | No | NULL | SVS | 2013-08-07 | 50 | 0 | MENASIGANAHALLI | 1 | NULL | 0 | 6209 | RAMANAGARA | 0
15 | 613 | 2484 | 59861 | 142161 | 5357163 | Drilling of Borewell to M.W.S Scheme at Menasiganahalli | 2012-2013 | PWS | Completed | 1.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | No | NULL | SVS | 2013-04-02 | 40 | 0 | MENASIGANAHALLI | 1 | NULL | 0 | 6209 | RAMANAGARA | 0